## simulated_veeva_vault_rim_data
Product | Submission ID | Secteur | Country | Submission Type | Start Date | Submission Date | HA Response Date | Status | HA Queries | Owner | Completion % | Planned Submission Date | index
GlacierC | SUB25720 | 5 | Other North | Renewal | 2024-01-01 | 2024-03-17 | 2024-04-26 | In Review | 0 | Janet S. | 95 | 2024-02-08 | 1
IceA | SUB87018 | 2 | North | Variation Type II | 2024-01-02 | 2024-02-28 | 2024-03-12 | In Review | 2 | Anna R. | 100 | 2024-03-25 | 2
SnowZ | SUB36838 | 6 | Also North | Variation Type II | 2024-01-02 | 2024-04-01 | 2024-04-27 | Rejected | 5 | Janet S. | 100 | 2024-03-24 | 3
IceA | SUB56865 | 3 | North Again | Initial MA | 2024-01-03 | 2024-04-25 | 2024-06-13 | Approved | 4 | Liu W. | 100 | 2024-02-19 | 4
SnowX | SUB32607 | 5 | Other North | Variation Type II | 2024-01-07 | 2024-04-17 | 2024-05-16 | Withdrawn | 2 | Liu W. | 90 | 2024-03-07 | 5
IceA | SUB94083 | 5 | Other North | Variation Type II | 2024-01-08 | 2024-04-21 | 2024-05-09 | In Review | 2 | Franz K. | 90 | 2024-03-10 | 6
GlacierC | SUB89244 | 1 | South | Renewal | 2024-01-11 | 2024-05-01 | 2024-06-28 | Rejected | 2 | Franz K. | 90 | 2024-03-06 | 7
SnowZ | SUB49805 | 2 | North | Initial MA | 2024-01-13 | 2024-03-02 | 2024-04-28 | Rejected | 4 | Anna R. | 100 | 2024-02-15 | 8
SnowX | SUB69171 | 5 | Other North | Renewal | 2024-01-13 | 2024-03-26 | 2024-04-09 | Approved | 1 | Marie D. | 95 | 2024-03-14 | 9
FrostB | SUB31615 | 1 | South | Variation Type II | 2024-01-13 | 2024-04-17 | 2024-05-10 | Rejected | 2 | Liu W. | 100 | 2024-04-10 | 10
GlacierC | SUB48939 | 3 | North Again | Renewal | 2024-01-17 | 2024-04-22 | 2024-06-13 | Approved | 0 | Janet S. | 100 | 2024-02-29 | 11
IcebergA | SUB10631 | 2 | North | Renewal | 2024-01-17 | 2024-03-07 | 2024-05-03 | Withdrawn | 0 | Franz K. | 95 | 2024-03-08 | 12
SnowX | SUB97000 | 4 | North Too | Initial MA | 2024-01-21 | 2024-03-20 | 2024-04-01 | Withdrawn | 4 | Anna R. | 90 | 2024-04-09 | 13
IceA | SUB56559 | 5 | Other North | Variation Type II | 2024-01-23 | 2024-02-28 | 2024-04-24 | Withdrawn | 0 | Liu W. | 100 | 2024-03-24 | 14
SnowZ | SUB70204 | 5 | Other North | Initial MA | 2024-01-24 | 2024-05-16 | 2024-07-06 | Rejected | 0 | Marie D. | 95 | 2024-03-11 | 15
IceA | SUB29169 | 6 | Also North | Initial MA | 2024-02-01 | 2024-04-09 | 2024-04-23 | Withdrawn | 5 | Franz K. | 90 | 2024-03-03 | 16
IceA | SUB14757 | 4 | North Too | Variation Type I | 2024-02-04 | 2024-04-21 | 2024-05-10 | Withdrawn | 2 | Liu W. | 100 | 2024-03-05 | 17
IcebergA | SUB27198 | 5 | Other North | Variation Type II | 2024-02-05 | 2024-05-23 | 2024-07-19 | In Review | 3 | Janet S. | 100 | 2024-03-08 | 18
IceA | SUB70313 | 1 | South | Variation Type I | 2024-02-06 | 2024-05-16 | 2024-07-03 | Withdrawn | 5 | Franz K. | 100 | 2024-03-23 | 19
SnowZ | SUB97670 | 4 | North Too | Variation Type I | 2024-02-06 | 2024-06-01 | 2024-07-27 | Withdrawn | 4 | Franz K. | 90 | 2024-04-05 | 20
GlacierC | SUB23480 | 3 | North Again | Variation Type II | 2024-02-06 | 2024-06-02 | 2024-07-20 | In Review | 2 | Marie D. | 95 | 2024-04-23 | 21
SnowX | SUB58303 | 7 | Still North | Renewal | 2024-02-07 | 2024-05-04 | 2024-06-11 | Rejected | 1 | Marie D. | 100 | 2024-04-29 | 22
SnowZ | SUB88029 | 3 | North Again | Initial MA | 2024-02-08 | 2024-03-17 | 2024-04-26 | Approved | 5 | Janet S. | 100 | 2024-03-10 | 23
SnowX | SUB34518 | 5 | Other North | Variation Type II | 2024-02-12 | 2024-04-15 | 2024-05-20 | In Review | 4 | Anna R. | 90 | 2024-04-18 | 24
SnowZ | SUB79548 | 4 | North Too | Variation Type I | 2024-02-12 | 2024-05-21 | 2024-07-08 | In Review | 1 | Franz K. | 95 | 2024-03-31 | 25
IceA | SUB55277 | 1 | South | Variation Type II | 2024-02-12 | 2024-04-07 | 2024-05-19 | Approved | 0 | Marie D. | 90 | 2024-05-09 | 26
SnowY | SUB39446 | 3 | North Again | Initial MA | 2024-02-14 | 2024-04-02 | 2024-05-12 | Withdrawn | 5 | Liu W. | 100 | 2024-04-11 | 27
SnowY | SUB60538 | 3 | North Again | Variation Type II | 2024-02-16 | 2024-05-23 | 2024-06-07 | Withdrawn | 2 | Anna R. | 90 | 2024-04-01 | 28
SnowY | SUB16950 | 6 | Also North | Variation Type I | 2024-02-18 | 2024-03-30 | 2024-05-03 | Approved | 1 | Janet S. | 90 | 2024-04-15 | 29
SnowX | SUB95040 | 5 | Other North | Variation Type I | 2024-02-20 | 2024-06-12 | 2024-07-03 | Approved | 1 | Anna R. | 100 | 2024-04-12 | 30
FrostB | SUB24091 | 3 | North Again | Variation Type I | 2024-02-21 | 2024-06-12 | 2024-07-15 | Rejected | 1 | Marie D. | 100 | 2024-05-18 | 31
SnowZ | SUB52354 | 7 | Still North | Initial MA | 2024-02-22 | 2024-06-19 | 2024-08-04 | Rejected | 1 | Janet S. | 100 | 2024-05-06 | 32
SnowZ | SUB88715 | 7 | Still North | Renewal | 2024-02-23 | 2024-05-31 | 2024-07-10 | Rejected | 2 | Marie D. | 95 | 2024-03-31 | 33
IceA | SUB23643 | 3 | North Again | Initial MA | 2024-02-27 | 2024-06-17 | 2024-08-01 | Rejected | 3 | Liu W. | 100 | 2024-04-30 | 34
GlacierC | SUB34517 | 3 | North Again | Variation Type II | 2024-02-28 | 2024-05-15 | 2024-06-19 | In Review | 5 | Anna R. | 90 | 2024-05-02 | 35
FrostB | SUB18173 | 4 | North Too | Variation Type I | 2024-03-06 | 2024-04-22 | 2024-05-04 | Approved | 1 | Franz K. | 100 | 2024-04-10 | 36
SnowX | SUB68928 | 1 | South | Renewal | 2024-03-08 | 2024-04-17 | 2024-06-07 | Approved | 1 | Liu W. | 100 | 2024-05-20 | 37
SnowZ | SUB84661 | 2 | North | Renewal | 2024-03-08 | 2024-05-10 | 2024-06-08 | In Review | 2 | Marie D. | 100 | 2024-05-12 | 38
GlacierC | SUB57469 | 5 | Other North | Renewal | 2024-03-08 | 2024-04-20 | 2024-06-03 | Rejected | 1 | Liu W. | 100 | 2024-05-24 | 39
SnowY | SUB73066 | 3 | North Again | Initial MA | 2024-03-09 | 2024-04-21 | 2024-05-22 | In Review | 2 | Franz K. | 100 | 2024-05-30 | 40
IceA | SUB58694 | 2 | North | Initial MA | 2024-03-10 | 2024-04-15 | 2024-05-04 | In Review | 1 | Liu W. | 100 | 2024-05-01 | 41
IcebergA | SUB55345 | 5 | Other North | Variation Type II | 2024-03-10 | 2024-07-01 | 2024-07-23 | Rejected | 2 | Anna R. | 100 | 2024-04-28 | 42
FrostB | SUB60107 | 2 | North | Variation Type I | 2024-03-10 | 2024-05-24 | 2024-06-09 | Withdrawn | 0 | Anna R. | 90 | 2024-04-23 | 43
SnowX | SUB67385 | 3 | North Again | Variation Type I | 2024-03-10 | 2024-06-09 | 2024-06-30 | Withdrawn | 2 | Marie D. | 90 | 2024-04-30 | 44
SnowY | SUB17659 | 6 | Also North | Variation Type I | 2024-03-11 | 2024-04-27 | 2024-06-04 | Rejected | 2 | Janet S. | 100 | 2024-04-19 | 45
SnowX | SUB78294 | 7 | Still North | Initial MA | 2024-03-11 | 2024-04-11 | 2024-06-01 | Rejected | 3 | Liu W. | 90 | 2024-05-11 | 46
GlacierC | SUB93060 | 2 | North | Renewal | 2024-03-12 | 2024-07-05 | 2024-07-24 | In Review | 1 | Marie D. | 100 | 2024-05-10 | 47
SnowY | SUB55810 | 2 | North | Variation Type II | 2024-03-20 | 2024-06-20 | 2024-08-15 | In Review | 1 | Liu W. | 100 | 2024-06-05 | 48
SnowX | SUB54626 | 4 | North Too | Renewal | 2024-03-20 | 2024-06-21 | 2024-07-26 | In Review | 1 | Anna R. | 100 | 2024-05-08 | 49
SnowY | SUB64114 | 6 | Also North | Renewal | 2024-03-20 | 2024-07-03 | 2024-07-18 | Withdrawn | 5 | Liu W. | 95 | 2024-06-08 | 50
SnowZ | SUB58853 | 7 | Still North | Variation Type II | 2024-03-22 | 2024-05-10 | 2024-06-12 | In Review | 2 | Marie D. | 100 | 2024-05-07 | 51
SnowY | SUB83973 | 1 | South | Variation Type I | 2024-03-26 | 2024-06-11 | 2024-07-27 | Rejected | 2 | Marie D. | 90 | 2024-04-30 | 52
SnowZ | SUB69203 | 4 | North Too | Variation Type II | 2024-03-28 | 2024-06-11 | 2024-07-10 | In Review | 4 | Marie D. | 95 | 2024-06-12 | 53
FrostB | SUB89674 | 3 | North Again | Variation Type I | 2024-04-01 | 2024-07-29 | 2024-08-30 | In Review | 4 | Liu W. | 95 | 2024-05-15 | 54
GlacierC | SUB24621 | 7 | Still North | Variation Type I | 2024-04-03 | 2024-05-11 | 2024-06-12 | Rejected | 0 | Marie D. | 100 | 2024-05-20 | 55
IcebergA | SUB56643 | 7 | Still North | Initial MA | 2024-04-04 | 2024-06-05 | 2024-06-26 | In Review | 0 | Janet S. | 100 | 2024-05-08 | 56
GlacierC | SUB90814 | 4 | North Too | Variation Type I | 2024-04-06 | 2024-06-16 | 2024-08-01 | Approved | 2 | Anna R. | 90 | 2024-06-14 | 57
SnowY | SUB42567 | 6 | Also North | Initial MA | 2024-04-10 | 2024-07-04 | 2024-08-24 | Approved | 1 | Franz K. | 100 | 2024-06-14 | 58
SnowY | SUB77136 | 1 | South | Variation Type II | 2024-04-11 | 2024-08-07 | 2024-09-09 | Approved | 2 | Anna R. | 100 | 2024-06-14 | 59
IcebergA | SUB97379 | 5 | Other North | Renewal | 2024-04-17 | 2024-06-19 | 2024-08-02 | Rejected | 3 | Franz K. | 90 | 2024-07-02 | 60
SnowX | SUB21131 | 6 | Also North | Variation Type II | 2024-04-19 | 2024-08-10 | 2024-09-06 | In Review | 5 | Franz K. | 100 | 2024-06-23 | 61
GlacierC | SUB73100 | 3 | North Again | Variation Type I | 2024-04-21 | 2024-07-13 | 2024-08-20 | In Review | 2 | Franz K. | 100 | 2024-07-11 | 62
GlacierC | SUB29091 | 6 | Also North | Variation Type I | 2024-04-26 | 2024-06-16 | 2024-07-13 | Approved | 3 | Janet S. | 90 | 2024-06-01 | 63
SnowX | SUB81683 | 1 | South | Variation Type I | 2024-05-01 | 2024-06-06 | 2024-07-14 | Approved | 5 | Anna R. | 100 | 2024-07-07 | 64
SnowZ | SUB77594 | 7 | Still North | Variation Type II | 2024-05-01 | 2024-07-19 | 2024-08-10 | In Review | 4 | Marie D. | 95 | 2024-07-06 | 65
SnowY | SUB18998 | 1 | South | Initial MA | 2024-05-03 | 2024-06-13 | 2024-08-02 | In Review | 0 | Marie D. | 95 | 2024-06-25 | 66
GlacierC | SUB41506 | 2 | North | Variation Type II | 2024-05-09 | 2024-06-30 | 2024-07-17 | Approved | 1 | Liu W. | 100 | 2024-07-06 | 67
IcebergA | SUB37079 | 1 | South | Variation Type II | 2024-05-10 | 2024-08-06 | 2024-10-01 | In Review | 4 | Janet S. | 90 | 2024-06-27 | 68
IcebergA | SUB90998 | 7 | Still North | Initial MA | 2024-05-16 | 2024-07-16 | 2024-09-10 | Approved | 4 | Liu W. | 90 | 2024-07-24 | 69
IcebergA | SUB65565 | 7 | Still North | Initial MA | 2024-05-16 | 2024-07-08 | 2024-08-23 | Approved | 0 | Anna R. | 100 | 2024-07-25 | 70
GlacierC | SUB48812 | 5 | Other North | Variation Type I | 2024-05-18 | 2024-09-02 | 2024-10-18 | In Review | 1 | Liu W. | 100 | 2024-08-03 | 71
IcebergA | SUB22070 | 1 | South | Variation Type II | 2024-05-19 | 2024-09-01 | 2024-10-16 | Rejected | 5 | Anna R. | 95 | 2024-06-22 | 72
SnowZ | SUB93365 | 7 | Still North | Initial MA | 2024-05-20 | 2024-06-19 | 2024-07-30 | In Review | 4 | Anna R. | 90 | 2024-07-09 | 73
SnowX | SUB76300 | 2 | North | Initial MA | 2024-05-20 | 2024-09-08 | 2024-09-23 | Rejected | 4 | Franz K. | 100 | 2024-06-28 | 74
SnowZ | SUB26889 | 2 | North | Initial MA | 2024-05-21 | 2024-07-14 | 2024-08-16 | Rejected | 4 | Marie D. | 100 | 2024-07-15 | 75
SnowY | SUB76352 | 3 | North Again | Variation Type II | 2024-05-23 | 2024-07-27 | 2024-09-25 | Approved | 5 | Franz K. | 100 | 2024-07-10 | 76
IceA | SUB20906 | 2 | North | Renewal | 2024-05-23 | 2024-09-02 | 2024-10-04 | In Review | 5 | Anna R. | 95 | 2024-07-24 | 77
SnowX | SUB57525 | 3 | North Again | Renewal | 2024-05-25 | 2024-09-10 | 2024-10-19 | Rejected | 2 | Marie D. | 95 | 2024-08-17 | 78
SnowX | SUB30766 | 4 | North Too | Variation Type I | 2024-05-25 | 2024-06-28 | 2024-08-09 | In Review | 4 | Franz K. | 100 | 2024-08-15 | 79
FrostB | SUB52965 | 5 | Other North | Initial MA | 2024-05-26 | 2024-06-30 | 2024-07-23 | In Review | 1 | Janet S. | 95 | 2024-07-10 | 80
SnowZ | SUB39159 | 1 | South | Variation Type II | 2024-06-02 | 2024-09-08 | 2024-09-30 | Approved | 5 | Liu W. | 100 | 2024-08-24 | 81
SnowY | SUB43717 | 3 | North Again | Renewal | 2024-06-04 | 2024-09-26 | 2024-11-13 | In Review | 0 | Liu W. | 100 | 2024-08-07 | 82
IcebergA | SUB88783 | 3 | North Again | Initial MA | 2024-06-04 | 2024-07-08 | 2024-07-21 | Withdrawn | 5 | Liu W. | 100 | 2024-08-10 | 83
SnowX | SUB46298 | 6 | Also North | Initial MA | 2024-06-05 | 2024-07-07 | 2024-08-28 | Withdrawn | 3 | Liu W. | 95 | 2024-08-21 | 84
FrostB | SUB70281 | 1 | South | Variation Type II | 2024-06-06 | 2024-09-02 | 2024-09-15 | Approved | 4 | Liu W. | 100 | 2024-08-01 | 85
IcebergA | SUB22448 | 1 | South | Variation Type II | 2024-06-07 | 2024-09-24 | 2024-11-15 | Withdrawn | 1 | Liu W. | 100 | 2024-07-08 | 86
SnowZ | SUB10971 | 4 | North Too | Variation Type I | 2024-06-07 | 2024-08-27 | 2024-09-10 | Rejected | 5 | Marie D. | 95 | 2024-08-23 | 87
SnowZ | SUB97093 | 6 | Also North | Variation Type II | 2024-06-07 | 2024-08-02 | 2024-08-29 | In Review | 1 | Janet S. | 90 | 2024-07-25 | 88
SnowZ | SUB50782 | 6 | Also North | Initial MA | 2024-06-07 | 2024-10-05 | 2024-10-26 | Rejected | 3 | Franz K. | 95 | 2024-09-03 | 89
IcebergA | SUB93130 | 7 | Still North | Variation Type I | 2024-06-11 | 2024-08-25 | 2024-09-21 | Withdrawn | 1 | Franz K. | 100 | 2024-08-10 | 90
IcebergA | SUB47738 | 3 | North Again | Variation Type II | 2024-06-12 | 2024-09-10 | 2024-11-02 | Approved | 4 | Janet S. | 100 | 2024-08-03 | 91
FrostB | SUB97593 | 1 | South | Initial MA | 2024-06-14 | 2024-08-13 | 2024-09-14 | Rejected | 5 | Janet S. | 100 | 2024-07-21 | 92
IceA | SUB50266 | 3 | North Again | Renewal | 2024-06-16 | 2024-10-01 | 2024-11-20 | In Review | 5 | Marie D. | 100 | 2024-08-14 | 93
SnowX | SUB24439 | 5 | Other North | Variation Type I | 2024-06-16 | 2024-08-25 | 2024-09-10 | Rejected | 5 | Janet S. | 100 | 2024-08-29 | 94
FrostB | SUB81010 | 2 | North | Renewal | 2024-06-17 | 2024-08-06 | 2024-09-27 | Approved | 1 | Franz K. | 90 | 2024-08-29 | 95
SnowZ | SUB76737 | 7 | Still North | Initial MA | 2024-06-18 | 2024-08-29 | 2024-09-30 | Withdrawn | 1 | Liu W. | 95 | 2024-08-19 | 96
SnowX | SUB63669 | 2 | North | Initial MA | 2024-06-19 | 2024-08-13 | 2024-09-18 | Approved | 0 | Liu W. | 100 | 2024-08-11 | 97
SnowZ | SUB99669 | 6 | Also North | Initial MA | 2024-06-20 | 2024-09-14 | 2024-10-30 | In Review | 3 | Franz K. | 100 | 2024-08-21 | 98
FrostB | SUB56254 | 2 | North | Renewal | 2024-06-20 | 2024-09-12 | 2024-10-28 | Approved | 0 | Franz K. | 100 | 2024-09-17 | 99
SnowX | SUB57495 | 3 | North Again | Variation Type I | 2024-06-26 | 2024-08-21 | 2024-09-21 | Withdrawn | 5 | Liu W. | 90 | 2024-08-28 | 100

## gantt
Assignee | ID | Phase | Task | Milestone | Start | End | Completion | Dependencies | Submission ID
Anna R. | 1 | Submission Planning | Submission Timeline Plan. | False | 2024-05-14 | 2024-05-20 | 82 |  | SUB93130
Anna R. | 2 | Document Preparation | Quality Check | False | 2024-09-15 | 2024-09-20 | 88 | 1 | SUB26889
Franz K. | 3 | Document Preparation | Dossier Compilation | True | 2024-05-20 | 2024-05-27 | 88 | 1 | SUB22070
Marie D. | 4 | Document Preparation | Quality Check | False | 2024-05-14 | 2024-05-17 | 52 |  | SUB63669
Franz K. | 5 | Regulatory Review | Approval Follow-up | False | 2024-05-14 | 2024-05-15 | 86 | 1 | SUB87018
Franz K. | 6 | Regulatory Review | HA Query Response | False | 2024-08-22 | 2024-08-25 | 75 | 3 | SUB68928
Anna R. | 7 | Regulatory Review | HA Query Response | False | 2024-08-25 | 2024-08-30 | 83 | 5 | SUB57495
Janet S. | 8 | Document Preparation | Final Review | False | 2024-08-18 | 2024-08-25 | 83 |  | SUB41506
Franz K. | 9 | Document Preparation | Final Review | False | 2024-05-07 | 2024-05-14 | 67 | 3 | SUB97379
Franz K. | 10 | Submission Planning | Regulatory Strategy Dev. | True | 2024-07-10 | 2024-07-17 | 95 |  | SUB88029
Franz K. | 11 | Document Preparation | Quality Check | True | 2024-04-06 | 2024-04-07 | 82 | 3 | SUB95040
Janet S. | 12 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-10 | 2024-08-16 | 97 |  | SUB70281
Marie D. | 13 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-28 | 2024-09-03 | 53 | 2 | SUB55345
Marie D. | 14 | Submission Planning | Submission Timeline Plan. | True | 2024-05-06 | 2024-05-12 | 99 |  | SUB48939
Marie D. | 15 | Regulatory Review | HA Query Response | False | 2024-07-05 | 2024-07-12 | 100 | 13 | SUB60107
Franz K. | 16 | Document Preparation | Final Review | False | 2024-04-29 | 2024-05-02 | 99 | 1 | SUB46298
Anna R. | 17 | Document Preparation | Final Review | False | 2024-05-24 | 2024-05-30 | 62 |  | SUB89674
Marie D. | 18 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-28 | 2024-08-29 | 53 | 4 | SUB24621
Janet S. | 19 | Submission Planning | Submission Timeline Plan. | False | 2024-08-27 | 2024-09-01 | 64 |  | SUB55345
Janet S. | 20 | Submission Planning | Submission Timeline Plan. | False | 2024-05-28 | 2024-06-03 | 70 |  | SUB37079
Janet S. | 21 | Regulatory Review | HA Query Response | False | 2024-07-30 | 2024-08-05 | 83 |  | SUB68928
Marie D. | 22 | Submission Planning | Regulatory Strategy Dev. | False | 2024-05-06 | 2024-05-12 | 66 |  | SUB77594
Franz K. | 23 | Document Preparation | Quality Check | False | 2024-09-02 | 2024-09-03 | 94 |  | SUB93365
Anna R. | 24 | Document Preparation | Quality Check | False | 2024-08-03 | 2024-08-09 | 76 |  | SUB93130
Anna R. | 25 | Document Preparation | Dossier Compilation | True | 2024-04-25 | 2024-04-28 | 94 | 13 | SUB52354
Franz K. | 26 | Submission Planning | Submission Timeline Plan. | False | 2024-04-26 | 2024-05-02 | 52 |  | SUB73066
Janet S. | 27 | Document Preparation | Final Review | False | 2024-08-01 | 2024-08-05 | 53 |  | SUB97093
Marie D. | 28 | Submission Planning | Submission Timeline Plan. | True | 2024-09-11 | 2024-09-14 | 81 |  | SUB58694
Franz K. | 29 | Regulatory Review | Submission to HA | True | 2024-04-13 | 2024-04-17 | 89 |  | SUB49805
Liu W. | 30 | Submission Planning | Submission Timeline Plan. | True | 2024-05-29 | 2024-05-30 | 95 |  | SUB89674
Janet S. | 31 | Document Preparation | Quality Check | True | 2024-07-20 | 2024-07-23 | 53 | 14 | SUB97093
Liu W. | 32 | Submission Planning | Regulatory Strategy Dev. | False | 2024-09-02 | 2024-09-06 | 69 |  | SUB58694
Anna R. | 33 | Regulatory Review | Submission to HA | True | 2024-04-12 | 2024-04-15 | 89 | 30 | SUB52354
Janet S. | 34 | Regulatory Review | Approval Follow-up | False | 2024-06-26 | 2024-07-03 | 81 | 1 | SUB58694
Anna R. | 35 | Submission Planning | Regulatory Strategy Dev. | False | 2024-06-24 | 2024-06-29 | 94 |  | SUB10971
Marie D. | 36 | Regulatory Review | Approval Follow-up | False | 2024-05-31 | 2024-06-03 | 65 |  | SUB93060
Franz K. | 37 | Document Preparation | Final Review | False | 2024-08-12 | 2024-08-18 | 78 |  | SUB90814
Franz K. | 38 | Submission Planning | Submission Timeline Plan. | False | 2024-09-20 | 2024-09-22 | 74 | 3 | SUB21131
Marie D. | 39 | Document Preparation | Quality Check | True | 2024-04-10 | 2024-04-14 | 72 | 14 | SUB54626
Liu W. | 40 | Regulatory Review | HA Query Response | False | 2024-08-26 | 2024-09-01 | 83 | 22 | SUB27198
Anna R. | 41 | Submission Planning | Submission Timeline Plan. | False | 2024-09-08 | 2024-09-11 | 75 | 15 | SUB97593
Janet S. | 42 | Submission Planning | Regulatory Strategy Dev. | False | 2024-04-01 | 2024-04-06 | 92 |  | SUB65565
Franz K. | 43 | Regulatory Review | HA Query Response | False | 2024-08-14 | 2024-08-18 | 86 | 5 | SUB24621
Janet S. | 44 | Document Preparation | Quality Check | False | 2024-05-05 | 2024-05-11 | 93 |  | SUB69203
Anna R. | 45 | Submission Planning | Submission Timeline Plan. | False | 2024-09-17 | 2024-09-21 | 73 |  | SUB39159
Janet S. | 46 | Submission Planning | Submission Timeline Plan. | False | 2024-05-27 | 2024-05-29 | 72 |  | SUB50782
Franz K. | 47 | Submission Planning | Submission Timeline Plan. | False | 2024-04-24 | 2024-04-27 | 50 | 19 | SUB58853
Marie D. | 48 | Regulatory Review | Approval Follow-up | False | 2024-06-18 | 2024-06-22 | 97 | 7 | SUB14757
Marie D. | 49 | Document Preparation | Final Review | True | 2024-07-04 | 2024-07-08 | 76 | 30 | SUB17659
Liu W. | 50 | Submission Planning | Regulatory Strategy Dev. | True | 2024-05-20 | 2024-05-22 | 91 | 33 | SUB97670
Liu W. | 51 | Regulatory Review | Submission to HA | False | 2024-07-09 | 2024-07-15 | 62 | 47 | SUB16950
Marie D. | 52 | Submission Planning | Regulatory Strategy Dev. | False | 2024-06-28 | 2024-07-01 | 52 | 25 | SUB20906
Anna R. | 53 | Submission Planning | Regulatory Strategy Dev. | False | 2024-07-30 | 2024-08-01 | 81 |  | SUB10971
Anna R. | 54 | Submission Planning | Submission Timeline Plan. | False | 2024-09-20 | 2024-09-23 | 79 | 41 | SUB88029
Franz K. | 55 | Submission Planning | Submission Timeline Plan. | False | 2024-08-04 | 2024-08-07 | 78 |  | SUB14757
Anna R. | 56 | Submission Planning | Regulatory Strategy Dev. | False | 2024-05-02 | 2024-05-03 | 83 | 29 | SUB50782
Liu W. | 57 | Regulatory Review | Approval Follow-up | False | 2024-09-21 | 2024-09-26 | 95 | 33 | SUB55345
Franz K. | 58 | Document Preparation | Final Review | False | 2024-09-12 | 2024-09-18 | 79 |  | SUB78294
Janet S. | 59 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-12 | 2024-08-15 | 53 |  | SUB58853
Anna R. | 60 | Document Preparation | Quality Check | False | 2024-09-26 | 2024-10-03 | 90 | 57 | SUB60538
Anna R. | 61 | Document Preparation | Quality Check | False | 2024-05-04 | 2024-05-05 | 93 |  | SUB57525
Anna R. | 62 | Document Preparation | Dossier Compilation | True | 2024-04-09 | 2024-04-11 | 87 |  | SUB29169
Janet S. | 63 | Document Preparation | Quality Check | False | 2024-08-06 | 2024-08-10 | 71 | 33 | SUB76352
Liu W. | 64 | Submission Planning | Submission Timeline Plan. | False | 2024-05-14 | 2024-05-19 | 90 |  | SUB58853
Janet S. | 65 | Submission Planning | Submission Timeline Plan. | True | 2024-07-20 | 2024-07-27 | 86 |  | SUB57469
Anna R. | 66 | Document Preparation | Final Review | False | 2024-04-01 | 2024-04-08 | 98 | 13 | SUB57469
Marie D. | 67 | Document Preparation | Quality Check | True | 2024-05-04 | 2024-05-09 | 57 | 30 | SUB81010
Marie D. | 68 | Document Preparation | Quality Check | False | 2024-05-30 | 2024-06-06 | 70 | 45 | SUB24621
Marie D. | 69 | Submission Planning | Submission Timeline Plan. | False | 2024-08-13 | 2024-08-19 | 88 | 14 | SUB77136
Liu W. | 70 | Submission Planning | Regulatory Strategy Dev. | False | 2024-07-14 | 2024-07-15 | 52 | 13 | SUB65565
Marie D. | 71 | Document Preparation | Quality Check | True | 2024-04-03 | 2024-04-07 | 51 |  | SUB90814
Anna R. | 72 | Submission Planning | Submission Timeline Plan. | True | 2024-05-28 | 2024-06-03 | 69 |  | SUB10631
Liu W. | 73 | Submission Planning | Submission Timeline Plan. | True | 2024-07-21 | 2024-07-23 | 57 | 15 | SUB27198
Franz K. | 74 | Document Preparation | Dossier Compilation | False | 2024-08-07 | 2024-08-08 | 66 |  | SUB22448
Anna R. | 75 | Submission Planning | Regulatory Strategy Dev. | True | 2024-04-11 | 2024-04-16 | 97 | 4 | SUB18173
Liu W. | 76 | Regulatory Review | HA Query Response | False | 2024-06-24 | 2024-06-25 | 98 | 45 | SUB88783
Marie D. | 77 | Document Preparation | Dossier Compilation | False | 2024-08-09 | 2024-08-12 | 82 | 57 | SUB97000
Marie D. | 78 | Submission Planning | Submission Timeline Plan. | False | 2024-05-06 | 2024-05-09 | 95 |  | SUB52965
Janet S. | 79 | Submission Planning | Submission Timeline Plan. | False | 2024-04-01 | 2024-04-04 | 78 | 22 | SUB79548
Liu W. | 80 | Document Preparation | Final Review | False | 2024-07-19 | 2024-07-23 | 92 | 49 | SUB30766
Marie D. | 81 | Regulatory Review | Submission to HA | False | 2024-09-05 | 2024-09-10 | 97 |  | SUB78294
Liu W. | 82 | Regulatory Review | HA Query Response | True | 2024-06-20 | 2024-06-23 | 96 |  | SUB32607
Janet S. | 83 | Regulatory Review | Submission to HA | True | 2024-09-02 | 2024-09-03 | 90 |  | SUB17659
Anna R. | 84 | Submission Planning | Submission Timeline Plan. | False | 2024-08-17 | 2024-08-24 | 61 | 71 | SUB57525
Marie D. | 85 | Regulatory Review | Approval Follow-up | False | 2024-05-24 | 2024-05-28 | 83 |  | SUB70204
Franz K. | 86 | Submission Planning | Submission Timeline Plan. | False | 2024-05-10 | 2024-05-16 | 82 | 37 | SUB56865
Marie D. | 87 | Submission Planning | Regulatory Strategy Dev. | False | 2024-06-20 | 2024-06-22 | 73 |  | SUB58853
Anna R. | 88 | Document Preparation | Quality Check | True | 2024-05-17 | 2024-05-18 | 62 | 13 | SUB58853
Anna R. | 89 | Document Preparation | Quality Check | False | 2024-06-10 | 2024-06-12 | 56 | 42 | SUB29169
Franz K. | 90 | Document Preparation | Final Review | True | 2024-05-18 | 2024-05-25 | 57 |  | SUB21131
Franz K. | 91 | Document Preparation | Quality Check | False | 2024-05-20 | 2024-05-27 | 56 | 40 | SUB37079
Anna R. | 92 | Submission Planning | Submission Timeline Plan. | False | 2024-09-21 | 2024-09-28 | 99 |  | SUB22448
Franz K. | 93 | Submission Planning | Regulatory Strategy Dev. | True | 2024-05-17 | 2024-05-18 | 74 | 35 | SUB93060
Anna R. | 94 | Document Preparation | Final Review | False | 2024-05-05 | 2024-05-12 | 75 | 56 | SUB14757
Franz K. | 95 | Regulatory Review | HA Query Response | False | 2024-08-20 | 2024-08-21 | 73 | 35 | SUB49805
Liu W. | 96 | Submission Planning | Regulatory Strategy Dev. | True | 2024-09-09 | 2024-09-13 | 59 | 31 | SUB60538
Liu W. | 97 | Submission Planning | Regulatory Strategy Dev. | False | 2024-06-01 | 2024-06-08 | 80 | 3 | SUB16950
Janet S. | 98 | Submission Planning | Submission Timeline Plan. | False | 2024-09-05 | 2024-09-11 | 90 | 89 | SUB73066
Anna R. | 99 | Regulatory Review | Submission to HA | False | 2024-07-01 | 2024-07-05 | 81 |  | SUB93060
Marie D. | 100 | Document Preparation | Quality Check | True | 2024-08-02 | 2024-08-05 | 77 |  | SUB93130
Anna R. | 101 | Regulatory Review | Approval Follow-up | True | 2024-06-11 | 2024-06-12 | 52 | 28 | SUB10631
Anna R. | 102 | Document Preparation | Dossier Compilation | False | 2024-09-27 | 2024-10-01 | 63 | 20 | SUB29091
Liu W. | 103 | Submission Planning | Submission Timeline Plan. | False | 2024-08-04 | 2024-08-05 | 58 | 43 | SUB22448
Janet S. | 104 | Document Preparation | Final Review | False | 2024-04-03 | 2024-04-04 | 56 | 28 | SUB56643
Janet S. | 105 | Regulatory Review | Submission to HA | True | 2024-07-13 | 2024-07-19 | 61 | 56 | SUB93365
Marie D. | 106 | Document Preparation | Quality Check | False | 2024-04-08 | 2024-04-13 | 84 | 54 | SUB58303
Franz K. | 107 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-06 | 2024-08-07 | 54 | 60 | SUB70281
Franz K. | 108 | Regulatory Review | HA Query Response | False | 2024-05-29 | 2024-06-02 | 75 | 106 | SUB58694
Janet S. | 109 | Submission Planning | Submission Timeline Plan. | False | 2024-06-26 | 2024-06-29 | 89 |  | SUB99669
Franz K. | 110 | Submission Planning | Regulatory Strategy Dev. | False | 2024-05-18 | 2024-05-24 | 73 | 63 | SUB17659
Franz K. | 111 | Submission Planning | Regulatory Strategy Dev. | True | 2024-09-23 | 2024-09-25 | 64 |  | SUB52965
Liu W. | 112 | Document Preparation | Quality Check | True | 2024-09-19 | 2024-09-20 | 95 |  | SUB55810
Liu W. | 113 | Document Preparation | Final Review | False | 2024-05-11 | 2024-05-16 | 78 |  | SUB97670
Liu W. | 114 | Submission Planning | Submission Timeline Plan. | False | 2024-06-10 | 2024-06-14 | 78 |  | SUB56643
Janet S. | 115 | Document Preparation | Quality Check | False | 2024-07-06 | 2024-07-09 | 86 | 6 | SUB17659
Anna R. | 116 | Regulatory Review | Submission to HA | False | 2024-05-04 | 2024-05-07 | 65 |  | SUB97670
Liu W. | 117 | Document Preparation | Quality Check | False | 2024-07-14 | 2024-07-21 | 50 | 18 | SUB24439
Janet S. | 118 | Document Preparation | Quality Check | False | 2024-09-09 | 2024-09-10 | 73 | 13 | SUB29169
Marie D. | 119 | Document Preparation | Dossier Compilation | False | 2024-08-26 | 2024-08-27 | 83 | 81 | SUB87018
Anna R. | 120 | Document Preparation | Final Review | False | 2024-09-15 | 2024-09-22 | 89 | 50 | SUB48812
Liu W. | 121 | Regulatory Review | HA Query Response | False | 2024-05-31 | 2024-06-07 | 66 |  | SUB55345
Janet S. | 122 | Document Preparation | Final Review | True | 2024-08-08 | 2024-08-13 | 59 |  | SUB27198
Janet S. | 123 | Submission Planning | Regulatory Strategy Dev. | False | 2024-06-14 | 2024-06-20 | 72 | 38 | SUB56254
Janet S. | 124 | Submission Planning | Submission Timeline Plan. | False | 2024-09-15 | 2024-09-22 | 97 |  | SUB81683
Janet S. | 125 | Regulatory Review | HA Query Response | False | 2024-07-14 | 2024-07-20 | 94 | 36 | SUB94083
Liu W. | 126 | Document Preparation | Quality Check | True | 2024-08-23 | 2024-08-26 | 71 | 120 | SUB10631
Franz K. | 127 | Submission Planning | Submission Timeline Plan. | False | 2024-06-20 | 2024-06-22 | 64 | 23 | SUB32607
Anna R. | 128 | Document Preparation | Final Review | True | 2024-04-09 | 2024-04-10 | 86 |  | SUB97000
Marie D. | 129 | Regulatory Review | Submission to HA | True | 2024-05-02 | 2024-05-04 | 62 |  | SUB65565
Marie D. | 130 | Submission Planning | Submission Timeline Plan. | False | 2024-04-17 | 2024-04-19 | 90 | 7 | SUB55277
Franz K. | 131 | Regulatory Review | HA Query Response | False | 2024-04-13 | 2024-04-15 | 89 |  | SUB67385
Marie D. | 132 | Document Preparation | Final Review | False | 2024-06-12 | 2024-06-19 | 96 |  | SUB31615
Anna R. | 133 | Regulatory Review | Approval Follow-up | False | 2024-04-06 | 2024-04-12 | 73 |  | SUB87018
Janet S. | 134 | Document Preparation | Final Review | False | 2024-09-15 | 2024-09-20 | 97 |  | SUB16950
Liu W. | 135 | Regulatory Review | HA Query Response | False | 2024-06-10 | 2024-06-17 | 94 |  | SUB10631
Franz K. | 136 | Document Preparation | Dossier Compilation | False | 2024-06-05 | 2024-06-10 | 61 |  | SUB57469
Janet S. | 137 | Submission Planning | Regulatory Strategy Dev. | False | 2024-09-12 | 2024-09-15 | 75 | 16 | SUB56865
Franz K. | 138 | Regulatory Review | Submission to HA | True | 2024-05-20 | 2024-05-27 | 82 | 70 | SUB70204
Marie D. | 139 | Regulatory Review | Submission to HA | False | 2024-04-08 | 2024-04-10 | 60 |  | SUB70313
Liu W. | 140 | Document Preparation | Quality Check | True | 2024-06-10 | 2024-06-16 | 100 | 101 | SUB89244
Marie D. | 141 | Document Preparation | Dossier Compilation | False | 2024-09-01 | 2024-09-02 | 64 |  | SUB55277
Marie D. | 142 | Document Preparation | Dossier Compilation | False | 2024-09-25 | 2024-09-29 | 85 | 60 | SUB56254
Franz K. | 143 | Submission Planning | Submission Timeline Plan. | True | 2024-07-31 | 2024-08-02 | 79 |  | SUB16950
Liu W. | 144 | Regulatory Review | Approval Follow-up | True | 2024-07-25 | 2024-07-27 | 71 |  | SUB46298
Janet S. | 145 | Submission Planning | Regulatory Strategy Dev. | True | 2024-05-25 | 2024-05-31 | 51 |  | SUB93365
Franz K. | 146 | Regulatory Review | Approval Follow-up | False | 2024-05-17 | 2024-05-23 | 70 | 59 | SUB70281
Liu W. | 147 | Regulatory Review | HA Query Response | False | 2024-06-20 | 2024-06-26 | 92 |  | SUB67385
Franz K. | 148 | Document Preparation | Dossier Compilation | True | 2024-05-13 | 2024-05-17 | 70 |  | SUB41506
Marie D. | 149 | Document Preparation | Quality Check | False | 2024-09-01 | 2024-09-06 | 72 | 64 | SUB90814
Liu W. | 150 | Submission Planning | Regulatory Strategy Dev. | True | 2024-07-21 | 2024-07-24 | 92 |  | SUB73100
Marie D. | 151 | Document Preparation | Quality Check | False | 2024-04-22 | 2024-04-26 | 53 |  | SUB65565
Janet S. | 152 | Regulatory Review | Approval Follow-up | True | 2024-07-13 | 2024-07-18 | 73 |  | SUB56643
Liu W. | 153 | Regulatory Review | HA Query Response | False | 2024-08-27 | 2024-08-29 | 56 | 144 | SUB60107
Liu W. | 154 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-14 | 2024-08-21 | 97 | 145 | SUB27198
Marie D. | 155 | Document Preparation | Final Review | False | 2024-07-21 | 2024-07-26 | 89 |  | SUB34518
Anna R. | 156 | Regulatory Review | HA Query Response | False | 2024-05-24 | 2024-05-25 | 97 | 37 | SUB22448
Janet S. | 157 | Document Preparation | Quality Check | False | 2024-04-13 | 2024-04-17 | 68 |  | SUB88783
Liu W. | 158 | Document Preparation | Quality Check | False | 2024-08-20 | 2024-08-25 | 52 |  | SUB90998
Liu W. | 159 | Regulatory Review | HA Query Response | False | 2024-05-07 | 2024-05-11 | 75 | 110 | SUB99669
Marie D. | 160 | Document Preparation | Quality Check | False | 2024-05-16 | 2024-05-17 | 51 |  | SUB55277
Marie D. | 161 | Regulatory Review | Submission to HA | False | 2024-05-31 | 2024-06-02 | 82 | 26 | SUB16950
Liu W. | 162 | Document Preparation | Quality Check | False | 2024-09-09 | 2024-09-13 | 55 | 142 | SUB79548
Marie D. | 163 | Regulatory Review | Submission to HA | False | 2024-04-10 | 2024-04-11 | 92 | 114 | SUB30766
Anna R. | 164 | Submission Planning | Regulatory Strategy Dev. | True | 2024-06-28 | 2024-07-01 | 88 |  | SUB32607
Franz K. | 165 | Submission Planning | Regulatory Strategy Dev. | True | 2024-07-28 | 2024-07-30 | 74 |  | SUB78294
Liu W. | 166 | Regulatory Review | HA Query Response | False | 2024-04-08 | 2024-04-12 | 51 |  | SUB65565
Janet S. | 167 | Regulatory Review | Approval Follow-up | False | 2024-07-28 | 2024-08-01 | 89 | 140 | SUB73100
Franz K. | 168 | Submission Planning | Submission Timeline Plan. | False | 2024-07-15 | 2024-07-18 | 50 | 40 | SUB97670
Liu W. | 169 | Submission Planning | Submission Timeline Plan. | True | 2024-04-18 | 2024-04-21 | 64 |  | SUB69203
Janet S. | 170 | Submission Planning | Regulatory Strategy Dev. | True | 2024-09-04 | 2024-09-06 | 77 |  | SUB31615
Anna R. | 171 | Regulatory Review | HA Query Response | False | 2024-09-24 | 2024-09-30 | 96 | 131 | SUB88715
Janet S. | 172 | Regulatory Review | Submission to HA | True | 2024-09-18 | 2024-09-21 | 70 |  | SUB57469
Liu W. | 173 | Submission Planning | Regulatory Strategy Dev. | False | 2024-04-01 | 2024-04-04 | 60 |  | SUB83973
Janet S. | 174 | Document Preparation | Final Review | False | 2024-06-21 | 2024-06-23 | 62 |  | SUB76300
Marie D. | 175 | Document Preparation | Quality Check | False | 2024-04-15 | 2024-04-16 | 93 | 126 | SUB95040
Franz K. | 176 | Submission Planning | Submission Timeline Plan. | False | 2024-04-01 | 2024-04-08 | 86 | 67 | SUB73066
Marie D. | 177 | Submission Planning | Submission Timeline Plan. | False | 2024-07-30 | 2024-08-05 | 52 | 26 | SUB77136
Marie D. | 178 | Regulatory Review | HA Query Response | False | 2024-07-28 | 2024-08-03 | 86 | 23 | SUB90814
Liu W. | 179 | Document Preparation | Quality Check | False | 2024-05-17 | 2024-05-22 | 100 |  | SUB27198
Franz K. | 180 | Submission Planning | Submission Timeline Plan. | False | 2024-09-17 | 2024-09-22 | 62 |  | SUB48939
Janet S. | 181 | Document Preparation | Dossier Compilation | False | 2024-04-19 | 2024-04-20 | 53 |  | SUB49805
Janet S. | 182 | Submission Planning | Submission Timeline Plan. | True | 2024-04-24 | 2024-04-28 | 75 |  | SUB36838
Anna R. | 183 | Regulatory Review | Approval Follow-up | True | 2024-04-25 | 2024-05-02 | 52 |  | SUB78294
Liu W. | 184 | Document Preparation | Dossier Compilation | True | 2024-09-23 | 2024-09-25 | 63 | 115 | SUB29169
Franz K. | 185 | Submission Planning | Regulatory Strategy Dev. | True | 2024-05-01 | 2024-05-07 | 97 | 54 | SUB26889
Anna R. | 186 | Document Preparation | Dossier Compilation | False | 2024-09-16 | 2024-09-17 | 74 | 129 | SUB23643
Janet S. | 187 | Document Preparation | Final Review | True | 2024-07-04 | 2024-07-09 | 92 |  | SUB10971
Janet S. | 188 | Submission Planning | Submission Timeline Plan. | False | 2024-05-04 | 2024-05-10 | 83 | 100 | SUB21131
Liu W. | 189 | Document Preparation | Final Review | False | 2024-07-24 | 2024-07-29 | 89 |  | SUB36838
Franz K. | 190 | Regulatory Review | HA Query Response | False | 2024-07-27 | 2024-07-29 | 61 | 86 | SUB89244
Marie D. | 191 | Submission Planning | Regulatory Strategy Dev. | False | 2024-08-11 | 2024-08-12 | 71 | 101 | SUB52965
Marie D. | 192 | Regulatory Review | Approval Follow-up | True | 2024-08-15 | 2024-08-17 | 66 |  | SUB39446
Anna R. | 193 | Submission Planning | Regulatory Strategy Dev. | True | 2024-06-09 | 2024-06-13 | 55 |  | SUB58303
Franz K. | 194 | Document Preparation | Final Review | False | 2024-04-29 | 2024-05-03 | 97 |  | SUB39159
Liu W. | 195 | Regulatory Review | Submission to HA | False | 2024-08-03 | 2024-08-08 | 94 | 192 | SUB14757
Anna R. | 196 | Submission Planning | Submission Timeline Plan. | False | 2024-05-16 | 2024-05-18 | 77 |  | SUB60538
Liu W. | 197 | Submission Planning | Regulatory Strategy Dev. | True | 2024-04-10 | 2024-04-16 | 80 | 126 | SUB24091
Marie D. | 198 | Regulatory Review | Approval Follow-up | True | 2024-08-19 | 2024-08-23 | 53 |  | SUB70281
Anna R. | 199 | Submission Planning | Submission Timeline Plan. | False | 2024-04-19 | 2024-04-21 | 62 | 198 | SUB10971
Anna R. | 200 | Regulatory Review | Submission to HA | False | 2024-08-19 | 2024-08-22 | 76 |  | SUB22448

## owners
Owner | link
Janet S. | https://imgur.com/IcF84k9.png
Anna R. | https://imgur.com/MoLRk6n.png
Liu W. | https://imgur.com/hJ4W7mi.png
Franz K. | https://imgur.com/rgcGD0i.png
Marie D. | https://imgur.com/qLf9kVM.png